## Sheet
Risk Prevention and Mitigation Activities Report
Reporting Period: 2018
Department: Inventory (Kilinto SEZ)
S/n | Addressed (Risk ID) | Prevention/Mitigation activity | Prevention/Mitigation activity description | Weight | Sub Activities Undertaken | Performance Metrics/indicators | Expected Outcome | Progress/Status in % | Budget Planned/Utilized | Challenges Encountered | Corrective Actions | Next action | Remark
1. | 5
|  | Establish safety stock levels for critical items | Set minimum stock levels to prevent shortages of essential inventory | 1 |  |  |  | 100% | ETB500.00/ETB699.98
[5 empty] | Identify critical inventory items | Critical items list documented and approved | Priority items requiring safety stock identified |  |  | challenge 333
|  | Implement real-time inventory monitoring system | Deploy automated system to track inventory levels and generate alerts | 1 |  |  |  | 25% | ETB0.00/ETB0.00
[5 empty] | Research and select inventory software | Software selection approved by management | Suitable inventory management system identified |  |  | challenge again | corrective 1
[5 empty] | Install and configure monitoring system | System installation completed successfully | Real-time inventory tracking operational |  |  | challenge 2 | corrective action
[5 empty] | Train staff on system usage | All inventory staff trained and certified | Staff proficient in using monitoring system
Date of Report: 2025-09-18
|  |  | Prepared By |  |  |  |  | Approved By
|  |  | Name: ___________________________ |  |  |  |  | Name: ___________________________
|  |  | Signature: ________________________ |  |  |  |  | Signature: ________________________
|  |  | Date: ____________________________ |  |  |  |  | Date: ____________________________